## Summary
ReKYC Automation Test Cases - 58 Active Scenarios
Scenario List Status | Formatted as requested
Total Active Scenarios | 58
Passed | 10
Failed | 1
Not Run | 47
Module | Status | Notes
Login + OTP | Formatted | Rows follow the exact sample format provided.
Nominee + Guardian | Added | Missing nominee/guardian scenarios are included.
Email/Mobile + Signature/IPV/eSign | Added | Remaining positive service flow scenarios are included.

## Test Cases
Step | Test Case ID | Module / Stage | Field / Control | Input / Condition | Test Steps | Expected Result | Status | Actual Result | Remarks
1 | NEG-LAUNCH-001 | Launch URL | Application URL | -- | Open ReKYC URL and verify login page load. | Login page should load successfully | PASS | Validated successfully in latest automation run
2 | NEG-LOGIN-001 | Login Page | UCC + DOB | Blank UCC, Blank DOB | Submit login form with blank UCC and blank DOB. | Validation message should display; stay on login page | PASS | Validated successfully in latest automation run
3 | NEG-LOGIN-002 | Login Page | UCC | Invalid UCC (INVALID123) | Enter invalid UCC and submit without DOB. | Validation/error message should display; stay on login page | PASS | Validated successfully in latest automation run
4 | NEG-LOGIN-003 | Login Page | UCC + DOB | Valid UCC + Wrong DOB | Enter valid UCC with wrong DOB and submit. | Login should fail; error shown; stay on login page | FAIL | No visible login validation feedback found | Known application validation gap: login is rejected but no visible validation message appears.
5 | NEG-LOGIN-004 | Login Page | UCC | Blank UCC + Valid DOB | Submit blank UCC with valid DOB. | Validation message should display; stay on login page | PASS | Validated successfully in latest automation run
6 | POS-LOGIN-000 | Login Page | Page Refresh | -- | Refresh login page before positive flow. | Page should reload cleanly before positive flow | PASS | Validated successfully in latest automation run
7 | POS-LOGIN-001 | Login Page | UCC | Valid UCC | Enter configured valid UCC. | UCC field should accept valid input | PASS | Validated successfully in latest automation run
8 | POS-LOGIN-002 | Login Page | DOB | -- | Click DOB field. | DOB calendar should open on click | PASS | Validated successfully in latest automation run
9 | POS-LOGIN-003 | Login Page | DOB | -- | Select configured valid DOB from calendar. | Valid DOB should be selectable from calendar | PASS | Validated successfully in latest automation run
10 | POS-LOGIN-004 | Login Page | Submit | -- | Submit valid login form. | Login form should submit and redirect to OTP page | PASS | Validated successfully in latest automation run
11 | POS-LOGIN-005 | OTP Page | Page URL | -- | Verify OTP page loaded. | URL should contain 'otp' after successful login | PASS | Validated successfully in latest automation run
12 | NEG-OTP-001 | OTP Verification | OTP | Blank OTP | Submit blank OTP on OTP verification page. | Validation message should display; stay on OTP page | Not Run | Pending latest automation run
13 | NEG-OTP-002 | OTP Verification | OTP | Wrong OTP (000000) | Enter wrong OTP and submit. | Invalid OTP message should display; stay on OTP page | Not Run | Pending latest automation run
14 | NEG-OTP-003 | OTP Verification | OTP | Short OTP (123) | Enter short OTP and submit. | Validation/error message should display; stay on OTP page | Not Run | Pending latest automation run
15 | POS-OTP-001 | OTP Verification | OTP | Valid OTP from Yopmail | Fetch valid OTP from Yopmail and enter it. | OTP should be fetched and entered successfully | Not Run | Pending latest automation run
16 | POS-OTP-002 | OTP Verification | Submit OTP | -- | Submit valid OTP. | Valid OTP submit should proceed past OTP page | Not Run | Pending latest automation run
17 | POS-DASH-001 | Dashboard | Page URL | -- | Verify dashboard page after OTP submission. | URL should NOT contain 'otp' after valid OTP submit | Not Run | Pending latest automation run
18 | POS-SECT-001 | Dashboard | Email Section | -- | Open Email section from dashboard. | Email section should open without error | Not Run | Pending latest automation run
19 | POS-SECT-002 | Dashboard | Mobile No Section | -- | Open Mobile No section from dashboard. | Mobile section should open without error | Not Run | Pending latest automation run
20 | POS-SECT-003 | Dashboard | Address Section | -- | Open Change of address section from dashboard. | Address section should open without error | Not Run | Pending latest automation run
21 | POS-SECT-004 | Dashboard | Nominee Section | -- | Open Nominee section from dashboard. | Nominee section should open without error | Not Run | Pending latest automation run
22 | POS-SECT-006 | Dashboard | Segment Section | -- | Open Segment section from dashboard. | Segment section should open without error | Not Run | Pending latest automation run
23 | POS-SECT-007 | Dashboard | Income Declaration | -- | Open Income Declaration section from dashboard. | Income Declaration section should open without error | Not Run | Pending latest automation run
24 | POS-SECT-008 | Dashboard | Dis Slip Req | -- | Open Dis Slip Req section from dashboard. | Dis Slip Req section should open without error | Not Run | Pending latest automation run
25 | POS-SECT-009 | Dashboard | Service Status | -- | Open Service Status section from dashboard. | Service Status section should open without error | Not Run | Pending latest automation run
26 | POS-SECT-010 | Dashboard | Documents Section | -- | Open Documents section from dashboard. | Documents section should open without error | Not Run | Pending latest automation run
27 | POS-SECT-011 | Documents | View Proof 1 | -- | Open first document proof and verify it is viewable. | First document proof should be viewable | Not Run | Pending latest automation run
28 | POS-SECT-012 | Documents | View Proof 2 | -- | Open second document proof and verify it is viewable. | Second document proof should be viewable | Not Run | Pending latest automation run
29 | POS-SECT-013 | Dashboard | DDPI Section | -- | Open DDPI section and verify page handling. | DDPI section should open (500 error handled gracefully) | Not Run | Pending latest automation run
30 | POS-NOM-001 | Nominee | Section Load | -- | Open nominee page and verify nominee controls are available. | Nominee page/form should load with nominee controls | Not Run | Pending latest automation run
31 | NEG-NOM-001 | Nominee | Submit | Blank nominee form | Submit blank nominee form. | Validation message should display for mandatory nominee fields | Not Run | Pending latest automation run
32 | NEG-NOM-002 | Nominee | PAN/Aadhaar Number | Invalid/short number | Enter invalid or short nominee PAN/Aadhaar number. | Validation message should display for invalid PAN/Aadhaar | Not Run | Pending latest automation run
33 | NEG-NOM-003 | Nominee | Nominee Name | 123456 | Enter numeric nominee name. | Validation message should display for invalid nominee name | Not Run | Pending latest automation run
34 | NEG-NOM-004 | Nominee | Mobile | 123 | Enter invalid nominee mobile number. | Validation message should display for invalid nominee mobile | Not Run | Pending latest automation run
35 | NEG-NOM-005 | Nominee | Relationship | Blank relationship | Leave nominee relationship blank and submit. | Validation message should display for missing relationship | Not Run | Pending latest automation run
36 | NEG-NOM-006 | Nominee | Share Percentage | 150 | Enter invalid nominee share percentage. | Validation message should display for invalid nominee share | Not Run | Pending latest automation run
37 | NEG-NOM-007 | Nominee | DOB | Future DOB | Enter future nominee DOB. | Validation message should display for invalid nominee DOB | Not Run | Pending latest automation run
38 | NEG-NOM-008 | Nominee | Email | bad-email | Enter invalid nominee email. | Validation message should display for invalid nominee email | Not Run | Pending latest automation run
39 | NEG-NOM-009 | Nominee | Guardian Details | Minor nominee, blank guardian | Select minor nominee and submit without guardian details. | Validation message should display for guardian fields | Not Run | Pending latest automation run
40 | POS-NOM-002 | Nominee | Nominee Details | Valid major nominee | Fill valid major nominee details and save. | Nominee form fields should accept and save valid major nominee data | Not Run | Pending latest automation run
41 | POS-NOM-003 | Nominee | Guardian Details | Valid minor nominee | Fill valid minor nominee with guardian details. | Minor nominee guardian fields should accept valid data | Not Run | Pending latest automation run
42 | POS-NOM-004 | Nominee | Save | Valid nominee flow | Save valid nominee flow and return to ReKYC. | Nominee details should save, then automation should return to ReKYC without e-Sign | Not Run | Pending latest automation run
43 | NEG-NOM-010 | Nominee | PAN/Aadhaar Number | Client Aadhaar (830889536550) | Enter client Aadhaar number as nominee PAN/Aadhaar. | Validation message should display when nominee Aadhaar is same as client Aadhaar | Not Run | Pending latest automation run
44 | NEG-NOM-011 | Nominee | PAN/Aadhaar Number | Client PAN (IBSPN7684H), then Continue | Enter client PAN as nominee PAN and click Continue. | Flow should not proceed when nominee PAN is same as client PAN | Not Run | Pending latest automation run
45 | NEG-GRD-001 | Guardian | PAN/Aadhaar Number | Invalid/short number | Enter invalid or short guardian PAN/Aadhaar number. | Validation message should display for invalid guardian PAN/Aadhaar | Not Run | Pending latest automation run
46 | NEG-GRD-002 | Guardian | Guardian Name | 123456 | Enter numeric guardian name. | Validation message should display for invalid guardian name | Not Run | Pending latest automation run
47 | NEG-GRD-003 | Guardian | Mobile | 123 | Enter invalid guardian mobile number. | Validation message should display for invalid guardian mobile | Not Run | Pending latest automation run
48 | NEG-GRD-004 | Guardian | DOB | Future DOB | Enter future guardian DOB. | Validation message should display for invalid guardian DOB | Not Run | Pending latest automation run
49 | NEG-GRD-005 | Guardian | Email | bad-email | Enter invalid guardian email. | Validation message should display for invalid guardian email | Not Run | Pending latest automation run
50 | NEG-GRD-006 | Guardian | Relationship | Blank relationship | Leave guardian relationship blank and submit. | Validation message should display for missing guardian relationship | Not Run | Pending latest automation run
51 | NEG-GRD-007 | Guardian | Continue | Click Continue after save | Click Continue after saved guardian nominee flow. | Flow should not proceed to e-Sign after saved guardian nominee | Not Run | Pending latest automation run
52 | POS-MOB-001 | Mobile No | OTP | Valid OTP via E-mail | Open Mobile No section, verify OTP, enter new mobile number, and submit valid OTP from Yopmail. | Mobile section should send OTP to E-mail and accept valid OTP from Yopmail | Not Run | Pending latest automation run
53 | POS-EMAIL-001 | Email | OTP | Valid OTP via E-mail | Open Email section, verify OTP, enter new email ID, and submit valid OTP from Yopmail. | Email section should send OTP to E-mail and accept valid OTP from Yopmail | Not Run | Pending latest automation run
54 | POS-SIGN-001 | Signature | Signature Upload | Signature.png | Upload Signature.png and submit signature. | Signature image should upload and submit successfully | Not Run | Pending latest automation run
55 | POS-PDF-001 | IPV/eSign | Unsigned KYC PDF | -- | Open and view unsigned KYC PDF. | Unsigned KYC PDF should open and be viewed before eSign | Not Run | Pending latest automation run
56 | POS-IPV-001 | IPV | Camera Capture | Fake blink camera | Complete IPV capture step and verify the flow advances. | IPV camera screen should capture or advance successfully | Not Run | Pending latest automation run
57 | POS-ESIGN-001 | eSign | Proceed to eSign | -- | Click Proceed to eSign and verify Protean page opens. | Protean Aadhaar eSign page should open | Not Run | Pending latest automation run
58 | POS-ESIGN-002 | eSign | Aadhaar OTP | 830889536550 | Enter Aadhaar number, fetch Aadhaar OTP from Yopmail, and submit. | Aadhaar OTP should be fetched from Yopmail and submitted | Not Run | Pending latest automation run